## Sheet1
ULS Scheduled AGIMP Crew Location - Week of 7/2/2018
Retirement Group | Ft of Main | Nbr of Services | Detour Required | PADOT TAD | Scheduled Start | Scheduled Finish | Street Name | From | To | Main Installation | Service Installation | Awaiting Restoration
Narberth A1 | 5825 | 116 | N | TAD4 TAD5 TAD8 TAD18 | 2018-04-06 | 2018-10-05 | Barrie Rd | Essex Ave | Cul-de-sac | x | x
[7 empty] | Elm Ter | Essex Ave | Cul-de-sac |  | x
[7 empty] | Essex Ave | Haverford Ave | Montgomery Ave |  | x
[7 empty] | Shady La | Wynnedale Ave | Montgomery Ave |  | x
[7 empty] | Stedney Pl | Essex Ave | Montgomery Ave |  | x
[7 empty] | Wynnedale Ave | Dudley Ave | Cul-de-sac |  | x
Narberth A2 | 3330 | 100 | N | TAD4 TAD5 TAD8 TAD18 | 2018-04-25 | 2018-10-05 | Forrest Ave | Haverford Ave | Woodbine Ave
[7 empty] | Woodbine Ave | Montgomery Ave | Essex Ave
Narberth A3 | 1900 | 69 | N | TAD4 TAD5 TAD8 TAD18 | 2018-06-07 | 2018-10-05 | Iona Ave | Lantwyn La | Montgomery Ave
[7 empty] | Meeting House La | Iona Ave | Montgomery Ave
[7 empty] | Williams Ave | Meeting House La | S/O Woodbine Ave
Narberth A4 | 1500 | 54 | N | TAD4 TAD5 TAD8 TAD18 | 2018-04-02 | 2018-10-05 | Hampden Ave | Haverford Rd | N/O Woodbine Ave |  |  | x
Narberth A5 | 515 | 20 | N | TAD4 TAD5 TAD8 TAD18 | 2018-07-10 | 2018-10-05 | Grayling Ave | Woodbine Ave | Price Ave | x
Narberth A6 | 4917 | 76 | N | TAD4 TAD5 TAD8 TAD18 | 2018-06-26 | 2018-10-05 | Narberth Ave | Montgomery Ave | Haverford Ave | X
[7 empty] | Price Ave | Narberth Ave | Grayling Ave
[7 empty] | Price Ave | Essex Ave | Narberth Ave |  |  | X
[7 empty] | Sabine Ave | Essex Ave | Montgomery Ave |  |  | X
[7 empty] | Wayne Ave | Narberth Ave | Essex Ave
Narberth A7 | 0 | 0 | N | TAD4 TAD5 TAD8 TAD18 | 2018-09-07 | 2018-10-05 | Haverford Ave | N Wynnewood Ave | Montgomery Ave
Narberth T1 | 274 | 0 | Y | TAD18 | 2018-06-18 | TBD | Wynnewood Ave | Woodside |  | X
Narberth T2 | 900 | 0 | Y | TAD18 | 2018-07-07 | TBD | E Wynnewood Ave | Woodside Ave | N Wynnewood Ave | X
ULS Planned AGIMP Crew Location - Week of 1/10/1900
Retirement Group | Ft of Main | Nbr of Services | Detour Required | PADOT TAD | Scheduled Start | Scheduled Finish | Street Name | From | To | Main Installation | Service Installation | Awaiting Restoration
Narberth A1 | 5825 | 116 | N | TAD4 TAD5 TAD8 TAD18 | 2018-04-06 | 2018-10-05 | Barrie Rd | Essex Ave | Cul-de-sac |  | X
[7 empty] | Elm Ter | Essex Ave | Cul-de-sac |  | X
[7 empty] | Essex Ave | Haverford Ave | Montgomery Ave |  | X
[7 empty] | Shady La | Wynnedale Ave | Montgomery Ave |  | X
[7 empty] | Stedney Pl | Essex Ave | Montgomery Ave |  | X
[7 empty] | Wynnedale Ave | Dudley Ave | Cul-de-sac |  | X
Narberth A2 | 3330 | 100 | N | TAD4 TAD5 TAD8 TAD18 | 2018-04-25 | 2018-10-05 | Forrest Ave | Haverford Ave | Woodbine Ave
[7 empty] | Woodbine Ave | Montgomery Ave | Essex Ave
Narberth A3 | 1900 | 69 | N | TAD4 TAD5 TAD8 TAD18 | 2018-06-07 | 2018-10-05 | Iona Ave | Lantwyn La | Montgomery Ave | X
[7 empty] | Meeting House La | Iona Ave | Montgomery Ave | X
[7 empty] | Williams Ave | Meeting House La | S/O Woodbine Ave | X
Narberth A4 | 1500 | 54 | N | TAD4 TAD5 TAD8 TAD18 | 2018-04-02 | 2018-10-05 | Hampden Ave | Haverford Rd | N/O Woodbine Ave |  |  | X
Narberth A5 | 515 | 20 | N | TAD4 TAD5 TAD8 TAD18 | 2018-07-10 | 2018-10-05 | Grayling Ave | Woodbine Ave | Price Ave
Narberth A6 | 4917 | 76 | N | TAD4 TAD5 TAD8 TAD18 | 2018-06-26 | 2018-10-05 | Narberth Ave | Montgomery Ave | Haverford Ave | X
[7 empty] | Price Ave | Narberth Ave | Grayling Ave
[7 empty] | Price Ave | Essex Ave | Narberth Ave |  |  | X
[7 empty] | Sabine Ave | Essex Ave | Montgomery Ave |  |  | X
[7 empty] | Wayne Ave | Narberth Ave | Essex Ave
Narberth A7 | 0 | 0 | N | TAD4 TAD5 TAD8 TAD18 | 2018-09-07 | 2018-10-05 | Haverford Ave | N Wynnewood Ave | Montgomery Ave
Narberth T1 | 274 | 0 | Y | TAD18 | 2018-06-18 | TBD | Wynnewood Ave | Woodside |  | X
Narberth T2 | 900 | 0 | Y | TAD18 | 2018-07-07 | TBD | E Wynnewood Ave | Woodside Ave | N Wynnewood Ave | X
Formulas:
Scheduled Start = INDEX('[1]2 - Schedule'!$A1:DU34,MATCH([Retirement Group],'[1]2 - Schedule'!$D1:D34,0),MATCH("Scheduled Start",'[1]2 - Schedule'!$A1:DU1,0))
Scheduled Finish = INDEX('[1]2 - Schedule'!$A1:DU34,MATCH([Retirement Group],'[1]2 - Schedule'!$D1:D34,0),MATCH("Scheduled Retirement Complete",'[1]2 - Schedule'!$A1:DU1,0))
Notes:
Streets highlighted in YELLOW = Main and/or Service crew working on street
Streets highlighed in BLUE = Main and Service work completed, waiting on PECO restoration
"Scheduled Finish" date is when gas construction is complete. Restoration to follow within 45-60 days (weather dependent).
Notes:
Streets highlighted in YELLOW = Main and/or Service crew working on street
Streets highlighed in BLUE = Main and Service work completed, waiting on PECO restoration
"Scheduled Finish" date is when gas construction is complete. Restoration to follow within 45-60 days (weather dependent).
Notes:
Streets highlighted in YELLOW = Main and/or Service crew working on street
Streets highlighed in BLUE = Main and Service work completed, waiting on PECO restoration
"Scheduled Finish" date is when gas construction is complete. Restoration to follow within 45-60 days (weather dependent).